## Summary & Scope
AECHELON TECHNOLOGY - ORLANDO FL ¦ DEMOLITION BID (DISASSEMBLE DYNAMICS, INC.)
Aechelon Technology - 12633 Challenger Parkway, Suite 250/260, Orlando FL 32826 ¦ GC: S.A. Casey Construction (Kelly Lehman) ¦ Romero Trumpp Farmer A1.01 / A1.02 (REV 1 10/06/26), List Engineering E1.00 / M1.00 / P1.00, Addenda #1 & #2 ¦ Proposal DDD-2026/1027R2
PRICE SUMMARY
BASE BID | 21790
Alternate No. 1 - carpet tile & vinyl base removal for new LVT (approx. 9,000 SF) | 5560
Unit price - each fluorescent fixture beyond the 153 counted | 45
SCOPE OF WORK (as written in the proposal)
OUR SCOPE OF WORK (INCLUSIONS)
Demo existing walls at office/corridor fronts to the extent required for new door/frame or glass system openings, 12 locations, +/-101 LF (Plan Note 1)
Demo existing interior partitions shown dashed, +/-175 LF (A1.01 Demolition Plan)
Demolish wall to the extent required for 1-hr construction upgrade, +/-40 LF (REV 1 A1.01 Note 7 / A1.02 Note 4)
Remove existing restroom plumbing fixtures (22 EA per P1.00), toilet partitions and finishes for refurbishment, 2 areas, +/-668 SF (Plan Note 2)
Carefully remove existing data server racks and set aside for owner relocation (Plan Note 3)
Remove existing door, frame and wall to the extent required for new 8'-0" door (Plan Note 5)
Remove existing casework and plumbing fixtures, including REF/DW casework run and 2 sinks, 3 locations, +/-25 LF (Plan Note 6; P1.00)
Remove existing ceiling grid and tile in areas shown, +/-2,371 SF; carefully remove and store acoustic ceiling tiles on site for reuse (Ceiling Note 3, RCP Gen. Note 1)
Remove existing light fixtures as tagged, 75 EA (61 lay-in / 14 linear pendant) (Ceiling Note 1)
Remove all remaining existing 2x4 fluorescent fixtures for LED swap, 78 EA (Addendum #2, Item 1)
Carefully remove existing track light, +/-12'-5", and turn over for relocation (Ceiling Note 2)
Remove existing electrical devices tagged DE (receptacles, data, switches, junction boxes / furniture feeds), 147 EA, including boxes, plates and wiring back to the nearest junction box (E1.00)
Remove existing flex duct at 17 locations and carefully remove existing grilles at 11 locations, set aside for reuse (M1.00 Keynotes 1 & 2)
Remove existing split system AH-1 with associated ductwork, controls and piping within the suite after refrigerant recovery and disconnect by others (M1.00 Keynote 3)
Coordinate salvage of any items with the owner before demolition (Demo Gen. Note 15)
Provide daily clean up of debris generated by demolition activities; leave demolition areas broom clean (Demo Gen. Note 12)
Removal and disposal of all construction debris (C&D) created from this work to an approved landfill accepting this debris per city, county & federal codes & EPA regulations.
All work conforms to state and local code requirements.
ADDED EXCLUSIONS
Existing water heater to remain (Plan Note 4); all work in hatched adjacent Business Group-B tenant areas.
Reinstalling or relocating server racks, track light and grilles; installing new LED fixtures or ceiling tile.
Removal of conduit and wiring beyond the nearest junction box or back to panel / source, panel schedule updates, make-safe and reconnects (E1.00 Notes 2 & 3); abandoned telephone / data cabling (by tenant vendor, Addendum #2 Item 13).
Refrigerant recovery, mechanical / electrical disconnects, capping of trunk ducts and piping, sealing of penetrations, rooftop condensing unit removal and any roof work (M1.00).
Plumbing disconnects, capping and removal of abandoned piping back to main (P1.00 Keynote 1; P0.01 Note 6).
Floor finish removal (carpet tile and vinyl base for new LVT per A6.00) is priced as Alternate No. 1.
Fluorescent fixtures beyond the 153 counted (75 tagged + 78 per Addendum #2) at $45.00 per EA.

## Inputs
Aechelon Technology - Orlando FL ¦ Demolition Estimate Inputs
Blue = editable input. Yellow = assumption to confirm. All costs flow to the Demo Bid tab.
Input | Value | Note
Labor rate ($/MH, flat) | 25 | Standing input
Crew size (men) | 6 | Standing input
Shift length (hrs) | 8 | Day work assumed (night work not included per proposal)
Profit ($ per crew-day) | 1000 | Standing input
Contingency (% of direct) | 5% | Standing input
C&D dumpster 30 yd ($/pull) | 350 | Orlando independent building / office park rate
Lodging ($/night, crew house) | 265 | Lake City to Orlando ~2.5 hrs each way
Per diem ($/man/day) | 40 | Standing input
Include lodging & per diem? (1 = yes, 0 = no) | 1 | Set to 0 if crew commutes daily
Lodging nights per crew-day | 1 | Short job - weeknights only

## Demo Bid - DDD
DISASSEMBLE DYNAMICS, INC. - DEMOLITION BID BREAKOUT
Aechelon Technology - 12633 Challenger Parkway, Suite 250/260, Orlando FL 32826 ¦ GC: S.A. Casey Construction (Kelly Lehman) ¦ Romero Trumpp Farmer A1.01 / A1.02 (REV 1 10/06/26), List Engineering E1.00 / M1.00 / P1.00, Addenda #1 & #2
Quantities scaled from A1.01 / A1.02 at 1/8" = 1'-0"; MEP counts from DE / keynote tags on E1.00, M1.00, P1.00 - see markup tabs. Verify in field. | [11 empty] | DEMOLITION MARKUPS - A1.01 / A1.02 (REV 1) + E1.00 / M1.00 / P1.00
# | Description | Ref | Qty | Unit | MH / Unit | MH | Labor $ | Equip / Rental $ | Disposal $ | Other $ | Direct $
BASE BID - ARCHITECTURAL SELECTIVE DEMOLITION (A1.01 / A1.02 REV 1)
D1 | Demo walls at office/corridor fronts for new door/frame or glass system openings, 12 locations (+/-101 LF) | Plan Note 1 | 101 | LF | 0.25 | 25.25 | 631.25 | 0 | 0 | 0 | 631.25
D2 | Demo interior partitions shown dashed (+/-175 LF) | A1.01 legend | 175 | LF | 0.25 | 43.75 | 1093.75 | 0 | 0 | 0 | 1093.75
D3 | Remove restroom plumbing fixtures (22 EA per P1.00), toilet partitions & finishes (after disconnect/cap by plumber), 2 areas | Plan Note 2; P1.00 KN1 | 668 | SF | 0.06 | 40.08 | 1002 | 0 | 0 | 0 | 1002
D4 | Carefully remove data server racks and set aside for owner relocation | Plan Note 3 | 1 | EA | 4 | 4 | 100 | 0 | 0 | 0 | 100
D5 | Remove door, frame & wall for new 8' door | Plan Note 5 | 1 | EA | 4 | 4 | 100 | 0 | 0 | 0 | 100
D6 | Remove casework & plumbing fixtures incl. REF/DW run and 2 sinks, 3 locations | Plan Note 6; P1.00 KN1 | 25 | LF | 0.4 | 10 | 250 | 0 | 0 | 0 | 250
D7 | Remove ceiling grid & tile - carefully remove and store ACT on site for reuse, 9 areas | Ceiling Note 3; RCP Gen. Note 1 | 2371 | SF | 0.02 | 47.42 | 1185.5 | 0 | 0 | 0 | 1185.5
D8 | Remove marked light fixtures (61 lay-in / 14 linear pendant) | Ceiling Note 1 | 75 | EA | 0.5 | 37.5 | 937.5 | 0 | 0 | 0 | 937.5
D8a | Remove all remaining existing 2x4 fluorescent fixtures for LED swap (moved from Alt 1 to base) | Addendum #2 Item 1; E2.01 | 78 | EA | 0.5 | 39 | 975 | 0 | 0 | 0 | 975
D9 | Carefully remove track light (+/-12'-5") and turn over for relocation | Ceiling Note 2 | 1 | EA | 1.5 | 1.5 | 37.5 | 0 | 0 | 0 | 37.5
D10 | Demolish wall to extent required for 1-hr construction upgrade (rated wall at former Open Work Area 121) | REV 1 A1.01 Note 7 / A1.02 Note 4 | 40 | LF | 0.3 | 12 | 300 | 0 | 0 | 0 | 300
D11 | Salvage coordination, load-out, protection of items to remain, broom clean | Demo Gen. Notes 8, 12, 15 | 1 | LS | 16 | 16 | 400 | 0 | 0 | 0 | 400
D12 | Ladders / baker scaffold / debris carts | - | 1 | LS | 0 | 0 | 0 | 300 | 0 | 0 | 300
D13 | Consumables - blades, bags, poly, PPE | - | 1 | LS | 0 | 0 | 0 | 0 | 0 | 400 | 400
BASE BID - MEP DEMOLITION (E1.00 / M1.00 / P1.00)
E1 | Remove electrical devices tagged DE (receptacles, data, switches, J-boxes / furniture feeds) incl. box, plate & wiring to nearest J-box | E1.00 Notes 1-3 | 147 | EA | 0.2 | 29.4 | 735 | 0 | 0 | 0 | 735
M1 | Remove existing flex duct (trunk capped by HVAC contractor) | M1.00 KN1 | 17 | EA | 0.35 | 5.95 | 148.75 | 0 | 0 | 0 | 148.75
M2 | Carefully remove existing grilles and stage on site for reuse | M1.00 KN2 | 11 | EA | 0.25 | 2.75 | 68.75 | 0 | 0 | 0 | 68.75
M3 | Remove split system AH-1 w/ associated ductwork, controls & piping inside suite (after refrigerant recovery & disconnect by others) | M1.00 KN3 | 1 | EA | 12 | 12 | 300 | 0 | 0 | 0 | 300
D14 | C&D disposal - 30 yd dumpsters | Demo Gen. Note 8 | 5 | PULL | 0 | 0 | 0 | 0 | 1750 | 0 | 1750
| BASE BID - man-hours / crew-days |  |  |  |  | 330.6 | 7
| Direct cost | [9 empty] | 10715
| Lodging & per diem | [9 empty] | 3535
| Contingency | [9 empty] | 535.75
| Profit ($/crew-day x crew-days) | [9 empty] | 7000
| BASE BID TOTAL | [9 empty] | 21790
ALTERNATE #1 - CARPET TILE & VINYL BASE REMOVAL FOR NEW LVT (A6.00 FINISH SCHEDULE)
A1.1 | Remove existing carpet tile in office areas receiving LVT-1 (adhesive left in place) | A6.00; Demo Gen. Note 13; site photos | 9000 | SF | 0.006 | 54 | 1350 | 0 | 0 | 0 | 1350
A1.2 | Remove existing vinyl wall base in same areas | A6.00 (VB-1) | 1500 | LF | 0.01 | 15 | 375 | 0 | 0 | 0 | 375
A1.3 | C&D disposal | - | 2 | PULL | 0 | 0 | 0 | 0 | 700 | 0 | 700
| ALT #1 - man-hours / crew-days |  |  |  |  | 69 | 2
| Direct cost | [9 empty] | 2425
| Lodging & per diem | [9 empty] | 1010
| Contingency | [9 empty] | 121.25
| Profit ($/crew-day x crew-days) | [9 empty] | 2000
| ALT #1 TOTAL | [9 empty] | 5560
| Unit price - each fluorescent fixture beyond the 153 counted ($/EA) | [9 empty] | 45
DEMOLITION BID SUMMARY
| BASE BID | [5 empty] | 7 |  |  |  | 21790
| ALT #1 | [5 empty] | 2 |  |  |  | 5560
| Base bid + Alt #1 (if accepted) | [9 empty] | 27350
EXPENSE BREAKDOWN BY COST TYPE
| Section | Labor MH | Labor $ | Equipment $ | Disposal $ | Other / Consumables $ | Lodging & Per Diem $ | Contingency $ | Profit $ | Total $
| BASE BID | 330.6 | 8265 | 300 | 1750 | 400 | 3535 | 535.75 | 7000 | 21790
| ALT #1 | 69 | 1725 | 0 | 700 | 0 | 1010 | 121.25 | 2000 | 5560
| % of base bid |  | 37.93% | 1.377% | 8.031% | 1.836% | 16.22% | 2.459% | 32.12% | 100%
Note on B9: Assumes wall tile in restrooms - included here as noted in inclusions
Note on B35: Approx. office area - excludes warehouse 121/123 (sealed concrete) and restrooms (PT-1). Verify at walk.
Note on L32: Rounded up to the next $10
Note on L43: Rounded up to the next $10

## Markup - A1.01 Demo Plan
MARKUP: A1.01 Demo Plan (full-size PDF: Aechelon_Demo_Markup_R2.pdf)

## Markup - A1.02 Demo RCP
MARKUP: A1.02 Demo RCP (full-size PDF: Aechelon_Demo_Markup_R2.pdf)

## Markup - E1.00 Elec Demo
MARKUP: E1.00 Elec Demo (full-size PDF: Aechelon_Demo_Markup_R2.pdf)

## Markup - M1.00 Mech Demo
MARKUP: M1.00 Mech Demo (full-size PDF: Aechelon_Demo_Markup_R2.pdf)

## Markup - P1.00 Plumb Demo
MARKUP: P1.00 Plumb Demo (full-size PDF: Aechelon_Demo_Markup_R2.pdf)