## Summary & Scope
AECHELON TECHNOLOGY - ORLANDO FL ¦ DEMOLITION BID (DISASSEMBLE DYNAMICS, INC.)
Aechelon Technology - 12633 Challenger Parkway, Suite 250/260, Orlando FL 32826 ¦ GC: S.A. Casey Construction (Kelly Lehman) ¦ Romero Trumpp Farmer Architects A1.01 / A1.02, Permit Set 09/14/2026 ¦ Proposal DDD-2026/1027R1
PRICE SUMMARY
BASE BID | 17630
Alternate No. 1 - remaining fluorescent fixtures throughout suite (approx. 60 EA) | 2660
Unit price - each fixture beyond 60 EA | 45
SCOPE OF WORK (as written in the proposal)
OUR SCOPE OF WORK (INCLUSIONS)
Demo existing walls at office/corridor fronts to the extent required for new door/frame or glass system openings, 12 locations, +/-101 LF (Plan Note 1)
Demo existing interior partitions shown dashed, +/-175 LF (A1.01 Demolition Plan)
Remove existing restroom plumbing fixtures, toilet partitions and finishes for refurbishment, 2 areas, +/-668 SF (Plan Note 2)
Carefully remove existing data server racks and set aside for owner relocation (Plan Note 3)
Remove existing door, frame and wall to the extent required for new 8'-0" door (Plan Note 5)
Remove existing casework and plumbing fixtures, including REF/DW casework run, 3 locations, +/-25 LF (Plan Note 6)
Remove existing ceiling grid and tile in areas shown, +/-2,371 SF; carefully remove and store acoustic ceiling tiles on site for reuse (Ceiling Note 3, RCP Gen. Note 1)
Remove existing light fixtures as tagged, 75 EA (61 lay-in / 14 linear pendant) (Ceiling Note 1)
Carefully remove existing track light, +/-12'-5", and turn over for relocation (Ceiling Note 2)
Disconnect and remove electrical devices, boxes, plates and wiring in demolished walls back to the nearest junction box (Demo Gen. Note 10)
Coordinate salvage of any items with the owner before demolition (Demo Gen. Note 15)
Provide daily clean up of debris generated by demolition activities; leave demolition areas broom clean (Demo Gen. Note 12)
Removal and disposal of all construction debris (C&D) created from this work to an approved landfill accepting this debris per city, county & federal codes & EPA regulations.
All work conforms to state and local code requirements.
ADDED EXCLUSIONS
Existing water heater to remain (Plan Note 4); all work in hatched adjacent Business Group-B tenant areas.
Reinstalling or relocating server racks and track light; installing new LED fixtures or ceiling tile.
Removal of conduit and wiring beyond the nearest junction box or back to panel / source (Demo Gen. Note 10).
Floor finish demolition - no finish schedule provided (Demo Gen. Note 13).
Removal of fluorescent fixtures beyond the 75 tagged is priced as Alternate No. 1 (RCP Gen. Note 3).

## Inputs
Aechelon Technology - Orlando FL ¦ Demolition Estimate Inputs
Blue = editable input. Yellow = assumption to confirm. All costs flow to the Demo Bid tab.
Input | Value | Note
Labor rate ($/MH, flat) | 25 | Standing input
Crew size (men) | 6 | Standing input
Shift length (hrs) | 8 | Day work assumed (night work not included per proposal)
Profit ($ per crew-day) | 1000 | Standing input
Contingency (% of direct) | 5% | Standing input
C&D dumpster 30 yd ($/pull) | 350 | Orlando independent building / office park rate
Lodging ($/night, crew house) | 265 | Lake City to Orlando ~2.5 hrs each way
Per diem ($/man/day) | 40 | Standing input
Include lodging & per diem? (1 = yes, 0 = no) | 1 | Set to 0 if crew commutes daily
Lodging nights per crew-day | 1 | Short job - weeknights only

## Demo Bid - DDD
DISASSEMBLE DYNAMICS, INC. - DEMOLITION BID BREAKOUT
Aechelon Technology - 12633 Challenger Parkway, Suite 250/260, Orlando FL 32826 ¦ GC: S.A. Casey Construction (Kelly Lehman) ¦ Romero Trumpp Farmer Architects A1.01 / A1.02, Permit Set 09/14/2026
Quantities scaled from A1.01 / A1.02 at 1/8" = 1'-0" - see markup tabs. Verify in field. | [11 empty] | DEMOLITION MARKUPS - A1.01 DEMO PLAN / A1.02 DEMO RCP
# | Description | Ref | Qty | Unit | MH / Unit | MH | Labor $ | Equip / Rental $ | Disposal $ | Other $ | Direct $
BASE BID - INTERIOR SELECTIVE DEMOLITION (A1.01 / A1.02)
D1 | Demo walls at office/corridor fronts for new door/frame or glass system openings, 12 locations (+/-101 LF) | Plan Note 1 | 101 | LF | 0.25 | 25.25 | 631.25 | 0 | 0 | 0 | 631.25
D2 | Demo interior partitions shown dashed (+/-175 LF) | A1.01 legend | 175 | LF | 0.25 | 43.75 | 1093.75 | 0 | 0 | 0 | 1093.75
D3 | Remove restroom plumbing fixtures, toilet partitions & finishes (after cap by plumber), 2 areas | Plan Note 2 | 668 | SF | 0.06 | 40.08 | 1002 | 0 | 0 | 0 | 1002
D4 | Carefully remove data server racks and set aside for owner relocation | Plan Note 3 | 1 | EA | 4 | 4 | 100 | 0 | 0 | 0 | 100
D5 | Remove door, frame & wall for new 8' door | Plan Note 5 | 1 | EA | 4 | 4 | 100 | 0 | 0 | 0 | 100
D6 | Remove casework & plumbing fixtures incl. REF/DW run, 3 locations | Plan Note 6 | 25 | LF | 0.4 | 10 | 250 | 0 | 0 | 0 | 250
D7 | Remove ceiling grid & tile - carefully remove and store ACT on site for reuse, 9 areas | Ceiling Note 3; RCP Gen. Note 1 | 2371 | SF | 0.02 | 47.42 | 1185.5 | 0 | 0 | 0 | 1185.5
D8 | Remove marked light fixtures (61 lay-in / 14 linear pendant) | Ceiling Note 1 | 75 | EA | 0.5 | 37.5 | 937.5 | 0 | 0 | 0 | 937.5
D9 | Carefully remove track light (+/-12'-5") and turn over for relocation | Ceiling Note 2 | 1 | EA | 1.5 | 1.5 | 37.5 | 0 | 0 | 0 | 37.5
D10 | Disconnect & remove devices, boxes, plates & wiring in demolished walls back to nearest J-box | Demo Gen. Note 10 | 276 | LF | 0.05 | 13.8 | 345 | 0 | 0 | 0 | 345
D11 | Salvage coordination, load-out, protection of items to remain, broom clean | Demo Gen. Notes 8, 12, 15 | 1 | LS | 16 | 16 | 400 | 0 | 0 | 0 | 400
D12 | Ladders / baker scaffold / debris carts | - | 1 | LS | 0 | 0 | 0 | 300 | 0 | 0 | 300
D13 | Consumables - blades, bags, poly, PPE | - | 1 | LS | 0 | 0 | 0 | 0 | 0 | 400 | 400
D14 | C&D disposal - 30 yd dumpsters | Demo Gen. Note 8 | 4 | PULL | 0 | 0 | 0 | 0 | 1400 | 0 | 1400
| BASE BID - man-hours / crew-days |  |  |  |  | 243.3 | 6
| Direct cost | [9 empty] | 8182.5
| Lodging & per diem | [9 empty] | 3030
| Contingency | [9 empty] | 409.125
| Profit ($/crew-day x crew-days) | [9 empty] | 6000
| BASE BID TOTAL | [9 empty] | 17630
ALTERNATE #1 - REMAINING FLUORESCENT FIXTURES THROUGHOUT SUITE (RCP GEN. NOTE 3)
A1.1 | Remove all remaining existing fluorescent fixtures throughout suite (not tagged) - approx. count | RCP Gen. Note 3 | 60 | EA | 0.5 | 30 | 750 | 0 | 0 | 0 | 750
A1.2 | C&D disposal | - | 1 | PULL | 0 | 0 | 0 | 0 | 350 | 0 | 350
| ALT #1 - man-hours / crew-days |  |  |  |  | 30 | 1
| Direct cost | [9 empty] | 1100
| Lodging & per diem | [9 empty] | 505
| Contingency | [9 empty] | 55
| Profit ($/crew-day x crew-days) | [9 empty] | 1000
| ALT #1 TOTAL | [9 empty] | 2660
| Unit price for fixtures beyond the approx. count ($/EA) | [9 empty] | 45
DEMOLITION BID SUMMARY
| BASE BID | [5 empty] | 6 |  |  |  | 17630
| ALT #1 | [5 empty] | 1 |  |  |  | 2660
| Base bid + Alt #1 | [9 empty] | 20290
EXPENSE BREAKDOWN BY COST TYPE
| Section | Labor MH | Labor $ | Equipment $ | Disposal $ | Other / Consumables $ | Lodging & Per Diem $ | Contingency $ | Profit $ | Total $
| BASE BID | 243.3 | 6082.5 | 300 | 1400 | 400 | 3030 | 409.125 | 6000 | 17630
| ALT #1 | 30 | 750 | 0 | 350 | 0 | 505 | 55 | 1000 | 2660
| % of base bid |  | 34.5% | 1.702% | 7.941% | 2.269% | 17.19% | 2.321% | 34.03% | 100%
Note on B9: Assumes wall tile in restrooms - included here as noted in inclusions
Note on B29: Count not tagged on A1.02 - approx. 60 EA scaled from the RCP; verify at walk
Note on L26: Rounded up to the next $10
Note on L36: Rounded up to the next $10

## Markup - A1.01 Demo Plan
MARKUP: A1.01 Demo Plan (full-size PDF: Aechelon_Demo_Markup.pdf)

## Markup - A1.02 Demo RCP
MARKUP: A1.02 Demo RCP (full-size PDF: Aechelon_Demo_Markup.pdf)