## Summary & Scope
HARBOR FREIGHT TOOLS - MOUNT PLEASANT PA ¦ DEMOLITION BID (DISASSEMBLE DYNAMICS, INC.)
Harbor Freight Tools - 819 Crossroads Plaza, Mount Pleasant PA 15666 ¦ GC: Marco Contractors (job key hft8841) ¦ ADA Architects D1.0 dated 09/14/26 ¦ 18,280 GSF former Save A Lot ¦ Bids were due 10/27/26 10:00 AM ET to Jayne Baxter, jbaxter@marcocontractors.com
PRICE SUMMARY
BASE BID - Interior + exterior/site demolition | 51100.4025
Alt #1 - CMU openings & infill removal | 7185.75
Alt #2 - Plumbing trench sawcut & slab removal | 3978.75
Alt #3 - Sawcutting at site removal limits | 2451
Alt #4 - Floor cut-outs & interior curb | 2424.75
Alt #5 - Mastic removal / grinding | 20137.125
SCOPE OF WORK
DEMOLITION SCOPE OF WORK
1. Remove all existing floor finishes throughout the HFT space, +/-18,060 SF (Plan Note 215, Gen. Note 16)
2. Remove fixtures (fixed or free-standing) and all abandoned equipment throughout the HFT space (Plan Notes 202, 203)
3. Remove light fixtures completely throughout the HFT space (Plan Note 212)
4. Remove abandoned electrical equipment not to be re-used incl. junction boxes, conduit and wiring, and unused wires and hangers, back to the nearest junction box (Plan Note 205, A2.0)
5. Remove exposed metal studs completely, +/-74 LF (+/-58'-8" and +/-14'-10") (Plan Note 207)
6. Remove existing gyp. bd. wall and associated furring (Plan Note 209)
7. Remove (2) existing overhead doors and frames and (1) hollow metal door and frame (Plan Notes 218, 221, 240)
8. Remove existing storefront doors and storefront system at new bi-parting entry, +/-12'-0" W x 10'-0" H, and portion of storefront +/-5'-2" W; knee wall to remain (Plan Notes 211, 219)
9. Remove existing canopy and all associated attachments at north door (Plan Note 247)
10. Remove existing signage (Plan Note 223)
11. Remove existing receiving platform, rail, canopy, ramp and all associated attachments, +/-871 SF (Plan Note 208)
12. Remove asphalt for new concrete pad and receiving enclosure, +/-911 SF, and existing sloped asphalt, +/-176 SF (Plan Notes 224, 227)
13. Remove concrete walk for new concrete ramp, frost slab, sidewalk and egress ramp, +/-916 SF (Plan Notes 225, 226, 228, 234)
14. Remove existing bollards completely, 4 EA (Plan Note 246)
15. Remove all debris from site and legally dispose; leave broom clean (Gen. Notes 2, 5, 21)
ALTERNATES
Alt #1: Cut and remove CMU to expand OH door opening to 8'-0" x 10'-0", masonry at bi-parting entry, (2) new 3'-4" x 7'-4" HM door openings, and remove 8" CMU infill, +/-150 SF (Plan Notes 218, 219, 220, 236)
Alt #2: Sawcut and remove slab for plumbing trench, approx. 370 SF (Plan Note 217)
Alt #3: Sawcut asphalt and concrete walk at site removal limits, +/-280 LF (Plan Notes 224-228, 234)
Alt #4: Cut out remaining floor outlets, drains and holes (allowance 10 EA) and sawcut/remove interior concrete curb +/-12 LF (Plan Notes 216, 249)
Alt #5: Grind / remove mastic after flooring removal (Plan Note 215)
EXCLUSIONS
- Roofing, roof deck openings and capped curb removal at new RTUs (Plan Notes 213, 214) - by landlord's roofing contractor / mechanical contractor
- Mechanical, plumbing, fire protection and electrical demolition by those trades (Gen. Notes 13, 14; M1.0, P1.0, E-sheets), except light fixtures and abandoned electrical back to the nearest junction box
- Removal of conduit and wiring beyond the nearest junction box or back to panel/source; utility disconnects, caps and off-hours shutdowns
- All patching, repair and prep: masonry wall patch, slab patch and prep for new finishes, concrete infill, opening prep for new masonry infill, demising wall prep, column paint prep (Plan Notes 201, 206-209, 211, 215-221, 236, 247, 249)
- Shoring included is limited to non-load-bearing masonry; load-bearing wall shoring, shoring design, structural engineering and stamped drawings excluded. NOTE: D1.0 states GC shoring must be in the bid with no exclusions
- Furnishing and installing lintels, bearing plates, jamb reinforcement and grouting; new masonry infill
- Excavation for new ramps, frost slab and sidewalks beyond removal of existing paving; private utility locates; slab X-ray / GPR scanning (Gen. Note 20)
- Downspout repair / rework (Plan Notes 245, 248); asphalt patching, seal coat and striping
- Items to remain (Plan Notes 200, 201, 206, 210, 222, 229-233, 235, 237-239, 241-245, 250, 251) and telco demarc
- Hazardous materials survey and abatement (Gen. Note 6)
- Bid assumes landlord scope complete prior to DDD mobilization; anything incomplete is by change order
- Terms: plans only, zero retainage, net 30, price valid 90 days; additional mobilization $3,250
OPEN ITEMS TO CONFIRM
- Bid date was 10/27/26 10:00 AM ET - confirm Marco will still accept a late number
- Travel job (~900 mi from Lake City): lodging & per diem included (toggle on Inputs); mobilization terms may need to exceed the standard $3,250
- Existing floor finish type and light fixture count not shown - verify at walk; receiving platform construction not detailed
- PA dumpster and equipment rates are placeholders - confirm locally

## Inputs
Harbor Freight Tools - Mount Pleasant PA ¦ Demolition Estimate Inputs
Blue = editable input. Yellow = assumption to confirm. All costs flow to the Demo Bid tab.
Input | Value | Note
Labor rate ($/MH, flat) | 25 | Standing input
Crew size (men) | 6 | Standing input
Shift length (hrs) | 8 | Day work; 8-week GC schedule starting 11/16/26
Profit ($ per crew-day) | 1000 | Standing input
Contingency (% of direct) | 5% | Standing input
C&D dumpster 30 yd ($/pull) | 650 | Mount Pleasant PA rate not on file - confirm with local hauler
Concrete/asphalt dumpster 20 yd ($/pull) | 550 | PA rate not on file - confirm
Lodging ($/night, crew house) | 265 | Standing Airbnb rate; travel job ~900 mi from Lake City
Per diem ($/man/day) | 40 | Standing input
Include lodging & per diem? (1 = yes, 0 = no) | 1 | Set to 0 if a local PA crew is used
Lodging nights per crew-day (incl. weekends) | 1.4 | 7 nights per 5 work days

## Demo Bid - DDD
DISASSEMBLE DYNAMICS, INC. - DEMOLITION BID BREAKOUT
Harbor Freight Tools - 819 Crossroads Plaza, Mount Pleasant PA 15666 ¦ GC: Marco Contractors (job key hft8841) ¦ ADA Architects D1.0 dated 09/14/26
Quantities scaled from D1.0 (3/32" = 1'-0") and plan dimensions - see markup tabs. Verify in field. | [11 empty] | DEMOLITION MARKUPS - D1.0 FULL SHEET, ENLARGED WEST, ENLARGED EAST
# | Description | Ref | Qty | Unit | MH / Unit | MH | Labor $ | Equip / Rental $ | Disposal $ | Other $ | Direct $
BASE BID - INTERIOR DEMOLITION
D1 | Remove all existing floor finishes throughout (DDD-owned scraper) | Note 215; Gen. Note 16 | 18060 | SF | 0.01 | 180.6 | 4515 | 0 | 0 | 0 | 4515
D2 | Remove fixtures (fixed or free-standing) and abandoned equipment throughout | Notes 202, 203 | 18060 | SF | 0.003 | 54.18 | 1354.5 | 0 | 0 | 0 | 1354.5
D3 | Remove light fixtures completely throughout HFT space (high-bay / strip at +/-16'-18') | Note 212 | 150 | EA | 0.5 | 75 | 1875 | 0 | 0 | 0 | 1875
D4 | Remove abandoned electrical (j-boxes, conduit, wire) and unused wires/hangers back to nearest J-box | Note 205; A2.0 | 18060 | SF | 0.004 | 72.24 | 1806 | 0 | 0 | 0 | 1806
D5 | Remove exposed metal studs completely (+/-58'-8" west wall, +/-14'-10" east), +/-16' high | Note 207 | 74 | LF | 0.25 | 18.5 | 462.5 | 0 | 0 | 0 | 462.5
D6 | Remove existing gyp. bd. wall and associated furring (+/-2' section, north wall) | Note 209 | 1 | EA | 3 | 3 | 75 | 0 | 0 | 0 | 75
D7 | Remove existing overhead doors & frames (west wall) | Notes 218, 240 | 2 | EA | 6 | 12 | 300 | 0 | 0 | 0 | 300
D8 | Remove existing hollow metal door & frame (north wall) | Note 221 | 1 | EA | 2 | 2 | 50 | 0 | 0 | 0 | 50
D9 | Remove storefront doors & system at new bi-parting entry (+/-12'-0") and storefront portion (+/-5'-2"), knee wall to remain | Notes 211, 219 | 17 | LF | 1 | 17 | 425 | 0 | 0 | 0 | 425
D10 | Remove existing canopy and attachments at north door | Note 247 | 1 | EA | 4 | 4 | 100 | 0 | 0 | 0 | 100
D11 | Remove existing exterior signage (coordinate with landlord) | Note 223 | 1 | LS | 8 | 8 | 200 | 0 | 0 | 0 | 200
D12 | Load-out, protection of items to remain (telco demarc, fire riser, gas meter, elec. equipment), broom clean | Gen. Notes 2, 11 | 1 | LS | 40 | 40 | 1000 | 0 | 0 | 0 | 1000
D13 | 26' scissor lift for lights / studs / signage | - | 8 | DAY | 0 | 0 | 0 | 1650 | 0 | 0 | 1650
D14 | Consumables - blades, debris carts, bags, poly, PPE | - | 1 | LS | 0 | 0 | 0 | 0 | 0 | 1200 | 1200
D15 | C&D disposal - 30 yd dumpsters | Gen. Note 5 | 6 | PULL | 0 | 0 | 0 | 0 | 3900 | 0 | 3900
| INTERIOR BASE BID - man-hours / crew-days |  |  |  |  | 486.52 | 11
| Direct cost | [9 empty] | 18913
| Lodging & per diem (crew-days x nights factor x lodging + crew x per diem x crew-days) | [9 empty] | 6721
| Contingency | [9 empty] | 945.65
| Profit ($/crew-day x crew-days) | [9 empty] | 11000
| INTERIOR BASE BID TOTAL | [9 empty] | 37579.65
BASE BID - EXTERIOR / SITE DEMOLITION
S1 | Remove existing receiving platform, rail, canopy, ramp and all attachments (west) | Note 208 | 871 | SF | 0.06 | 52.26 | 1306.5 | 0 | 0 | 0 | 1306.5
S2 | Remove asphalt for new concrete pad and receiving enclosure (west, net of platform) | Note 224 | 911 | SF | 0.01 | 9.11 | 227.75 | 0 | 0 | 0 | 227.75
S3 | Remove existing sloped asphalt (east) | Note 227 | 176 | SF | 0.012 | 2.112 | 52.8 | 0 | 0 | 0 | 52.8
S4 | Remove concrete walk for new egress ramp, accessible ramp, frost slab and sidewalk (east) | Notes 225, 226, 228, 234 | 916 | SF | 0.03 | 27.48 | 687 | 0 | 0 | 0 | 687
S5 | Remove existing bollards completely | Note 246 | 4 | EA | 2 | 8 | 200 | 0 | 0 | 0 | 200
S6 | Skid steer w/ breaker (4 days) + mini-excavator (3 days) incl. delivery | - | 1 | LS | 0 | 0 | 0 | 3600 | 0 | 0 | 3600
S7 | Concrete / asphalt disposal - 20 yd dumpsters (+/-45 tons) | - | 4 | PULL | 0 | 0 | 0 | 0 | 2200 | 0 | 2200
| SITE BASE BID - man-hours / crew-days |  |  |  |  | 98.962 | 3
| Direct cost | [9 empty] | 8274.05
| Lodging & per diem (crew-days x nights factor x lodging + crew x per diem x crew-days) | [9 empty] | 1833
| Contingency | [9 empty] | 413.7025
| Profit ($/crew-day x crew-days) | [9 empty] | 3000
| SITE BASE BID TOTAL | [9 empty] | 13520.7525
ALTERNATE #1 - CMU OPENINGS & INFILL REMOVAL
A1.1 | Cut & remove CMU: expand OH door opening to 8'x10' (218), masonry at bi-parting entry (219), (2) new 3'-4"x7'-4" HM openings (220), remove 8" CMU infill (236) | Notes 218, 219, 220, 236 | 150 | SF | 0.5 | 75 | 1875 | 0 | 0 | 0 | 1875
A1.2 | Wall saw / chainsaw rental & blades | - | 3 | DAY | 0 | 0 | 0 | 1350 | 0 | 0 | 1350
A1.3 | CMU disposal - 20 yd dumpster | - | 1 | PULL | 0 | 0 | 0 | 0 | 550 | 0 | 550
| ALT #1 - man-hours / crew-days |  |  |  |  | 75 | 2
| Direct cost | [9 empty] | 3775
| Lodging & per diem (crew-days x nights factor x lodging + crew x per diem x crew-days) | [9 empty] | 1222
| Contingency | [9 empty] | 188.75
| Profit ($/crew-day x crew-days) | [9 empty] | 2000
| ALT #1 TOTAL | [9 empty] | 7185.75
ALTERNATE #2 - PLUMBING TRENCH SAWCUT & SLAB REMOVAL
A2.1 | Sawcut slab for plumbing trench | Note 217 | 270 | LF | 0.05 | 13.5 | 337.5 | 900 | 0 | 0 | 1237.5
A2.2 | Break & remove trench slab (approx. 370 SF per plan; +/-374 SF scaled) - excavation by plumber | Note 217 | 374 | SF | 0.05 | 18.7 | 467.5 | 0 | 0 | 0 | 467.5
A2.3 | Concrete disposal - 20 yd dumpster | - | 1 | PULL | 0 | 0 | 0 | 0 | 550 | 0 | 550
| ALT #2 - man-hours / crew-days |  |  |  |  | 32.2 | 1
| Direct cost | [9 empty] | 2255
| Lodging & per diem (crew-days x nights factor x lodging + crew x per diem x crew-days) | [9 empty] | 611
| Contingency | [9 empty] | 112.75
| Profit ($/crew-day x crew-days) | [9 empty] | 1000
| ALT #2 TOTAL | [9 empty] | 3978.75
ALTERNATE #3 - SAWCUTTING AT SITE REMOVAL LIMITS
A3.1 | Sawcut asphalt / concrete walk at removal limits | Notes 224-228, 234 | 280 | LF | 0.05 | 14 | 350 | 450 | 0 | 0 | 800
| ALT #3 - man-hours / crew-days |  |  |  |  | 14 | 1
| Direct cost | [9 empty] | 800
| Lodging & per diem (crew-days x nights factor x lodging + crew x per diem x crew-days) | [9 empty] | 611
| Contingency | [9 empty] | 40
| Profit ($/crew-day x crew-days) | [9 empty] | 1000
| ALT #3 TOTAL | [9 empty] | 2451
ALTERNATE #4 - FLOOR CUT-OUTS & INTERIOR CURB
A4.1 | Cut out remaining floor outlets, drains, holes (allowance 10 EA) - concrete infill by others | Note 216 | 10 | EA | 1.5 | 15 | 375 | 250 | 0 | 0 | 625
A4.2 | Sawcut and remove interior concrete curb | Note 249 | 12 | LF | 0.5 | 6 | 150 | 0 | 0 | 0 | 150
| ALT #4 - man-hours / crew-days |  |  |  |  | 21 | 1
| Direct cost | [9 empty] | 775
| Lodging & per diem (crew-days x nights factor x lodging + crew x per diem x crew-days) | [9 empty] | 611
| Contingency | [9 empty] | 38.75
| Profit ($/crew-day x crew-days) | [9 empty] | 1000
| ALT #4 TOTAL | [9 empty] | 2424.75
ALTERNATE #5 - MASTIC REMOVAL / GRINDING AFTER FLOORING REMOVAL
A5.1 | Grind / remove mastic after flooring removal (HFT vendor polishing by others) | Note 215 | 18060 | SF | 0.015 | 270.9 | 6772.5 | 3200 | 0 | 0 | 9972.5
| ALT #5 - man-hours / crew-days |  |  |  |  | 270.9 | 6
| Direct cost | [9 empty] | 9972.5
| Lodging & per diem (crew-days x nights factor x lodging + crew x per diem x crew-days) | [9 empty] | 3666
| Contingency | [9 empty] | 498.625
| Profit ($/crew-day x crew-days) | [9 empty] | 6000
| ALT #5 TOTAL | [9 empty] | 20137.125
DEMOLITION BID SUMMARY
| INTERIOR BASE BID | [5 empty] | 11 |  |  |  | 37579.65
| SITE BASE BID | [5 empty] | 3 |  |  |  | 13520.7525
| ALT #1 | [5 empty] | 2 |  |  |  | 7185.75
| ALT #2 | [5 empty] | 1 |  |  |  | 3978.75
| ALT #3 | [5 empty] | 1 |  |  |  | 2451
| ALT #4 | [5 empty] | 1 |  |  |  | 2424.75
| ALT #5 | [5 empty] | 6 |  |  |  | 20137.125
| Base bid (interior + site) | [9 empty] | 51100.4025
| Base bid + all alternates | [9 empty] | 87277.7775
EXPENSE BREAKDOWN BY COST TYPE
| Section | Labor MH | Labor $ | Equipment $ | Disposal $ | Other / Consumables $ | Lodging & Per Diem $ | Contingency $ | Profit $ | Total $
| INTERIOR BASE BID | 486.52 | 12163 | 1650 | 3900 | 1200 | 6721 | 945.65 | 11000 | 37579.65
| SITE BASE BID | 98.962 | 2474.05 | 3600 | 2200 | 0 | 1833 | 413.7025 | 3000 | 13520.7525
| ALT #1 | 75 | 1875 | 1350 | 550 | 0 | 1222 | 188.75 | 2000 | 7185.75
| ALT #2 | 32.2 | 805 | 900 | 550 | 0 | 611 | 112.75 | 1000 | 3978.75
| ALT #3 | 14 | 350 | 450 | 0 | 0 | 611 | 40 | 1000 | 2451
| ALT #4 | 21 | 525 | 250 | 0 | 0 | 611 | 38.75 | 1000 | 2424.75
| ALT #5 | 270.9 | 6772.5 | 3200 | 0 | 0 | 3666 | 498.625 | 6000 | 20137.125
| Base bid (interior + site) | 585.482 | 14637.05 | 5250 | 6100 | 1200 | 8554 | 1359.3525 | 14000 | 51100.4025
| Base bid + all alternates | 998.582 | 24964.55 | 11400 | 7200 | 1200 | 15275 | 2238.2275 | 25000 | 87277.7775
| % of base bid |  | 28.64% | 10.27% | 11.94% | 2.348% | 16.74% | 2.66% | 27.4% | 100%
| Unit check - base bid $ per building SF (18,280 GSF) | [9 empty] | 2.7954
Note on B7: Existing floor type not shown (former Save A Lot) - assumed VCT/resilient on slab. Mastic grind = Alt #5
Note on B9: Count not shown - assumed ~1 fixture per 120 SF; verify at walk
Note on B30: Platform construction not detailed - priced as concrete slab/dock on fill with steel rail & canopy; verify at walk
Note on B45: Exterior walls assumed load-bearing; shoring of load-bearing walls, lintels and bearing plates excluded
Note on H96: Crew-days

## Markup - D1.0 Demo Plan
MARKUP: D1.0 Demo Plan (full-size PDF: HFT_Mt_Pleasant_Demo_Markup.pdf)

## Markup - West Enlarged
MARKUP: West Enlarged (full-size PDF: HFT_Mt_Pleasant_Demo_Markup.pdf)

## Markup - East Enlarged
MARKUP: East Enlarged (full-size PDF: HFT_Mt_Pleasant_Demo_Markup.pdf)