## Bid Breakout
DISASSEMBLE DYNAMICS, INC. - DEMOLITION BID BREAKOUT
Orange County Corrections - FDC Isolation Cell Renovations in Units F & G (Solicitation Y25-790-RC) ¦ 3503 Vision Blvd, Orlando FL ¦ 10/27/2026
Quantities scaled from 100% CDs (05/22/2024) & RFI log thru Add. #32 - verify in field. Blue = input; black = formula.
# | Description | Ref (sheet / keynote) | Qty | Unit | MH / Unit | Base MH | Adj MH (w/ security) | Labor $ | Equip / Rental $ | Disposal $ | Material / Other $ | Direct Cost $
BASE BID - SELECTIVE DEMOLITION (ARCHITECTURAL, MECHANICAL, PLUMBING, FIRE PROTECTION, ELECTRICAL, FIRE ALARM)
B1 | Remove detention plumbing fixtures & all accessories (WC, lav, combo fixture) | AD201F/G D07; PD111F/G KN1 | 34 | EA | 2.5 | 85 | 106.25 | 2656.25 | 0 | 0 | 0 | 2656.25
B2 | Remove restroom / shower partitions & shower drains | AD201F/G D04; PD111F/G KN3 | 2 | LS | 16 | 32 | 40 | 1000 | 0 | 0 | 0 | 1000
B3 | Remove existing plaster ceiling (incl. security mesh where present) | AD201F/G legend; RFI #29 | 1065 | SF | 0.04 | 42.6 | 53.25 | 1331.25 | 0 | 0 | 0 | 1331.25
B4 | Remove door, frame & all accessories | AD201F D09 | 1 | EA | 4 | 4 | 5 | 125 | 0 | 0 | 0 | 125
B5 | Remove above-slab sanitary/vent piping incl. 4" line to VTR & VTR | PD111F/G KN1, KN5 | 450 | LF | 0.12 | 54 | 67.5 | 1687.5 | 0 | 0 | 0 | 1687.5
B6 | Remove domestic piping, valves & controls in chases / walls | PD112F/G KN2 | 500 | LF | 0.12 | 60 | 75 | 1875 | 0 | 0 | 0 | 1875
B7 | Remove surface-mounted SS pipe enclosures (entire) & valve control cabinet | PD112F/G KN1, KN3 | 3 | EA | 8 | 24 | 30 | 750 | 0 | 0 | 0 | 750
B8 | Remove AHU + supply & OA ductwork as req'd for new AHU | MD111F/G KN2; ED111G KN2 | 2 | EA | 16 | 32 | 40 | 1000 | 0 | 0 | 0 | 1000
B9 | Remove RTU + return duct transition (piping disconnected by mech) | MD112F/G KN2 | 2 | EA | 20 | 40 | 50 | 1250 | 0 | 0 | 0 | 1250
B10 | Remove roof exhaust / supply fans (curbs & security bars remain) | MD113F/G KN1-3 | 4 | EA | 5 | 20 | 25 | 625 | 0 | 0 | 0 | 625
B11 | Remove ductwork, 12x12 exhaust duct, supply & return grilles, hangers | MD111F/G, MD112F/G | 300 | LF | 0.15 | 45 | 56.25 | 1406.25 | 0 | 0 | 0 | 1406.25
B12 | Remove 2" CHWS&R piping back to 3" reducer (supports remain) | MD111G KN3 | 40 | LF | 0.15 | 6 | 7.5 | 187.5 | 0 | 0 | 0 | 187.5
B13 | Remove sprinkler branch piping & heads (after drain-down by FP) | FPD111, FPD112 | 360 | LF | 0.1 | 36 | 45 | 1125 | 0 | 0 | 0 | 1125
B14 | Remove light fixtures | ED111F/G, ED112F/G | 80 | EA | 0.75 | 60 | 75 | 1875 | 0 | 0 | 0 | 1875
B15 | Remove AHU / EF disconnects, devices, conduit & wire back to nearest J-box | ED111G, ED112G, ED113F/G; ED Gen. Note 2 | 1 | LS | 32 | 32 | 40 | 1000 | 0 | 0 | 0 | 1000
B16 | Remove fire alarm devices (system kept live by FA contractor) | FAD111F/G, FAD112F/G | 24 | EA | 0.5 | 12 | 15 | 375 | 0 | 0 | 0 | 375
B17 | Debris carry-down from Level 2 (no elevator), daily haul-out, tool / debris accounting | RFI #40, #43; 01 1100 1.9 | 1 | LS | 48 | 48 | 60 | 1500 | 300 | 0 | 0 | 1800
B18 | Dust & noise control: tacky mats, poly at openings, HEPA vacs, broom clean nightly | 02 4113 1.4.G; AD201 Gen. Note W | 1 | LS | 40 | 40 | 50 | 1250 | 400 | 0 | 1200 | 2850
B19 | Security onboarding: FDLE Level 1 checks & badging / orientation | 01 1100 1.9 | 1 | LS | 24 | 24 | 30 | 750 | 0 | 0 | 450 | 1200
B20 | C&D debris disposal - 30 yd dumpsters | 02 4113 3.5 | 4 | PULL | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 1400
| BASE BID - adjusted man-hours | [5 empty] | 870.75
| BASE BID - crew-days (MH / crew / shift) | [5 empty] | 19
| Direct cost (labor + equip + disposal + material) | [10 empty] | 25518.75
| Lodging & per diem | [10 empty] | 9595
| Contingency | [10 empty] | 1275.9375
| Profit ($/crew-day x crew-days) | [10 empty] | 19000
| BASE BID TOTAL | [10 empty] | 55389.6875
ALTERNATE #1 - CMU WALL REMOVAL (8" SOLID GROUTED)
A1.1 | Remove 8" solid grouted CMU chase walls - Level 1 (+/-166 LF x 10'-8") | SD111F/G Note 4; AD201F/G D01 | 1770 | SF | 0.2 | 354 | 442.5 | 11062.5 | 0 | 0 | 0 | 11062.5
A1.2 | Remove 8" solid grouted CMU walls - Level 2 (+/-62 LF x 9') | SD112F/G Note 4; AD202F/G D02 | 560 | SF | 0.28 | 156.8 | 196 | 4900 | 0 | 0 | 0 | 4900
A1.3 | Cut dowels flush at walls where slab remains | SD111F/G Note 4; SD501 A1 | 60 | LF | 0.15 | 9 | 11.25 | 281.25 | 0 | 0 | 0 | 281.25
A1.4 | Concrete chainsaw / wall saw rental + blades/chains | - | 12 | DAY | 0 | 0 | 0 | 0 | 5400 | 0 | 0 | 5400
A1.5 | CMU disposal - 20 yd concrete dumpsters (+/-93 tons) | - | 4 | PULL | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 1400
| ALTERNATE #1 - adjusted man-hours | [5 empty] | 649.75
| ALTERNATE #1 - crew-days (MH / crew / shift) | [5 empty] | 14
| Direct cost (labor + equip + disposal + material) | [10 empty] | 23043.75
| Lodging & per diem | [10 empty] | 7070
| Contingency | [10 empty] | 1152.1875
| Profit ($/crew-day x crew-days) | [10 empty] | 14000
| ALTERNATE #1 TOTAL | [10 empty] | 45265.9375
ALTERNATE #2 - SLAB-ON-GRADE, THICKENED SLAB & FOOTING REMOVAL
A2.1 | Sawcut slab-on-grade perimeter (4" SOG) | SD111F/G Notes 3; AD D11, D13 | 420 | LF | 0.04 | 16.8 | 21 | 525 | 0 | 0 | 0 | 525
A2.2 | Break & remove 4" slab-on-grade | SD111F/G (F +/-555 SF, G +/-569 SF) | 1124 | SF | 0.067 | 75.308 | 94.135 | 2353.375 | 0 | 0 | 0 | 2353.375
A2.3 | Remove thickened slab, footings & cont. bars at chase walls | SD501 A4, A6 | 8 | CY | 4 | 32 | 40 | 1000 | 0 | 0 | 0 | 1000
A2.4 | Walk-behind slab saw + electric breakers rental, blades | - | 4 | DAY | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 1200
A2.5 | Concrete disposal - 20 yd dumpsters (+/-44 tons) | - | 2 | PULL | 0 | 0 | 0 | 0 | 0 | 700 | 0 | 700
| ALTERNATE #2 - adjusted man-hours | [5 empty] | 155.135
| ALTERNATE #2 - crew-days (MH / crew / shift) | [5 empty] | 4
| Direct cost (labor + equip + disposal + material) | [10 empty] | 5778.375
| Lodging & per diem | [10 empty] | 2020
| Contingency | [10 empty] | 288.9187
| Profit ($/crew-day x crew-days) | [10 empty] | 4000
| ALTERNATE #2 TOTAL | [10 empty] | 12087.2938
ALTERNATE #3 - CONCRETE / PRECAST CUTTING, CORING & OPENINGS
A3.1 | Wall / slab cuts for new plumbing | AD201F D03 (4), AD201G (3), AD202F/G (2) | 9 | EA | 4 | 36 | 45 | 1125 | 0 | 0 | 0 | 1125
A3.2 | Partial CMU wall demo for new door opening | AD201F D10 | 1 | EA | 8 | 8 | 10 | 250 | 0 | 0 | 0 | 250
A3.3 | 12" deep openings in existing 10" precast wall panels | SD111F/G, SD112F/G, SD501 1 | 4 | EA | 6 | 24 | 30 | 750 | 0 | 0 | 0 | 750
A3.4 | Precast mezzanine slab openings at duct (max 9"x9") | SD112F/G | 2 | EA | 5 | 10 | 12.5 | 312.5 | 0 | 0 | 0 | 312.5
A3.5 | Holes in prestressed precast roof panels (max 9"x9") + metal deck opening | SD121; SD501 1 | 3 | EA | 5 | 15 | 18.75 | 468.75 | 0 | 0 | 0 | 468.75
A3.6 | Core drill / wall saw rental | - | 3 | DAY | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 600
A3.7 | GPR / X-ray scanning sub (load-bearing & prestressed elements) | RFI #32; S502; 01 7329 | 1 | LS | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000
| ALTERNATE #3 - adjusted man-hours | [5 empty] | 116.25
| ALTERNATE #3 - crew-days (MH / crew / shift) | [5 empty] | 3
| Direct cost (labor + equip + disposal + material) | [10 empty] | 6506.25
| Lodging & per diem | [10 empty] | 1515
| Contingency | [10 empty] | 325.3125
| Profit ($/crew-day x crew-days) | [10 empty] | 3000
| ALTERNATE #3 TOTAL | [10 empty] | 11346.5625
ALTERNATE #4 - GRIND DOWELS 1/2" BELOW TOP OF SLAB
A4.1 | Grind dowels / wall base 1/2" min below slab (repair by others) | SD111F/G Note 4 | 60 | LF | 0.25 | 15 | 18.75 | 468.75 | 150 | 0 | 0 | 618.75
| ALTERNATE #4 - adjusted man-hours | [5 empty] | 18.75
| ALTERNATE #4 - crew-days (MH / crew / shift) | [5 empty] | 1
| Direct cost (labor + equip + disposal + material) | [10 empty] | 618.75
| Lodging & per diem | [10 empty] | 505
| Contingency | [10 empty] | 30.9375
| Profit ($/crew-day x crew-days) | [10 empty] | 1000
| ALTERNATE #4 TOTAL | [10 empty] | 2154.6875
ALTERNATE #5 - NEGATIVE AIR & FULL-HEIGHT DUST CONTAINMENT
A5.1 | Negative air machines (2) + full-height poly containment per unit | 02 4113 1.4.G; Gen. Note W | 2 | UNIT | 24 | 48 | 60 | 1500 | 700 | 0 | 600 | 2800
| ALTERNATE #5 - adjusted man-hours | [5 empty] | 60
| ALTERNATE #5 - crew-days (MH / crew / shift) | [5 empty] | 2
| Direct cost (labor + equip + disposal + material) | [10 empty] | 2800
| Lodging & per diem | [10 empty] | 1010
| Contingency | [10 empty] | 140
| Profit ($/crew-day x crew-days) | [10 empty] | 2000
| ALTERNATE #5 TOTAL | [10 empty] | 5950
BID SUMMARY
| Item | [5 empty] | Crew-days |  |  |  |  | Price
| Base Bid - Selective Demolition (non-concrete / non-masonry) | [5 empty] | 19 |  |  |  |  | 55389.6875
| Alt #1 - CMU WALL REMOVAL (8" SOLID GROUTED) | [5 empty] | 14 |  |  |  |  | 45265.9375
| Alt #2 - SLAB-ON-GRADE, THICKENED SLAB & FOOTING REMOVAL | [5 empty] | 4 |  |  |  |  | 12087.2938
| Alt #3 - CONCRETE / PRECAST CUTTING, CORING & OPENINGS | [5 empty] | 3 |  |  |  |  | 11346.5625
| Alt #4 - GRIND DOWELS 1/2" BELOW TOP OF SLAB | [5 empty] | 1 |  |  |  |  | 2154.6875
| Alt #5 - NEGATIVE AIR & FULL-HEIGHT DUST CONTAINMENT | [5 empty] | 2 |  |  |  |  | 5950
| BASE BID + ALL ALTERNATES | [5 empty] | 43 |  |  |  |  | 132194.1688
| Unit-price check: Alt #1 CMU price / CMU SF | vs. Shawn's $18-24/SF reinforced non-bearing range | [9 empty] | 19.4274
Note on B7: 16 WC + 16 lav + 2 combo; chase-mounted stainless
Note on B9: Hatch area F +/-535 SF, G +/-530 SF
Note on B11: Roof patch by others
Note on B14: After disconnect / make-safe by trades
Note on B15: Assumes rigged by hand - no crane
Note on B20: 23+17+23+17
Note on B23: Equip = debris carts / buggies
Note on B26: Fixtures, piping, duct, plaster, lights
Note on B36: F +/-81 LF, G +/-85 LF
Note on B37: Debris carried down stairs
Note on B38: Grind 1/2" below slab = Alt #4
Note on B65: Lintels / jamb reinf. by others
Note on B68: Roof patch / curbs by others
Note on B70: Allowance - get scanning quote
Note on B90: Equip = 2 NAMs x ~2 wks per unit

## Inputs
FDC Isolation Cell Renovations - Units F & G ¦ Demolition Bid Inputs
Blue = editable input. Yellow = key assumption to confirm. All costs flow to 'Bid Breakout'.
Input | Value | Source / note
Labor rate ($/MH, flat - no night uptick) | 25 | Shawn standing input: $25/hr flat
Crew size (men) | 6 | Night crew
Shift length (hrs) | 8 | Base bid = night work Mon-Fri (01 2300); 01 1100 1.7.A daytime hrs = Alt No. 1
Security / productivity factor on labor | 25% | Escorts, vestibules, tool & debris accounting, no storage after hours (01 1100 1.9, RFI #43)
Profit ($ per crew-day) | 1000 | Shawn standing input: $1,000/day
Contingency (% of direct cost) | 5% | Shawn standing input: 5%
C&D dumpster ($/pull) | 350 | Orlando independent bldg rule $350/pull - confirm hauler can service FDC secure lot
Concrete/CMU dumpster ($/pull, 20 yd) | 350 | Orlando rate assumed = C&D; ~24 tons per full load
Lodging ($/night, crew house) | 265 | Lake City to Orlando ~2.5 hrs each way; night shifts
Per diem ($/man/day) | 40 | Shawn standing input
Include lodging & per diem? (1 = yes, 0 = no) | 1 | Set to 0 if crew commutes
FDLE Level 1 background check ($/man) | 75 | 01 1100 1.9 - contractor pays; ~2 wk turnaround (RFI #64)

## Scope of Work
DEMOLITION SCOPE OF WORK - FDC Isolation Cell Renovations in Units F & G
DEMOLITION SCOPE OF WORK
1 | Remove existing detention plumbing fixtures and all accessories - 16 WC, 16 lavatories, 2 combination fixtures (Plan Note D07, Plumbing Note 1)
2 | Remove existing restroom / shower partitions and shower drains, Units F & G (Plan Note D04, Plumbing Note 3)
3 | Remove existing plaster ceilings in hatched areas incl. security mesh where present, +/-1,065 SF (Plan Legend, RFI #29)
4 | Remove existing door, frame and all accessories, Unit F, 1 EA (Plan Note D09)
5 | Remove all above-slab sanitary and vent piping in hatched areas incl. 4" sanitary line up to and including the 4" VTR, Units F & G (Plumbing Notes 1, 5)
6 | Remove all domestic plumbing in chases and walls incl. valves, fixtures and associated controls, surface-mounted stainless steel pipe enclosures in their entirety, and the existing valve control cabinet (Plumbing Notes 1, 2, 3)
7 | Remove existing AHUs and portions of supply and outdoor air ductwork as required for new AHUs, 2 EA (Mech Note 2, Elec Note 2)
8 | Remove existing RTUs and return duct transitions after chilled water and condensate piping are disconnected by mechanical, 2 EA (Mech Note 2)
9 | Remove existing roof exhaust and supply fans, curbs and security bars to remain, 4 EA (Mech Notes 1, 2, 3)
10 | Remove existing supply / return grilles and associated ductwork, hangers, straps and supports, incl. 12x12 exhaust duct to 2nd floor (Mech Notes 1, 7, 9)
11 | Remove 2" CHWS&R piping back to 3" reducer, supports to remain, Unit G (Mech Note 3)
12 | Remove sprinkler branch piping and heads shown for demolition, +/-360 LF, after drain-down by the fire protection contractor (FPD111, FPD112)
13 | Remove existing light fixtures, 80 EA (ED111F/G, ED112F/G)
14 | Remove AHU and exhaust fan disconnect switches, devices, cabling and conduit back to the nearest junction box, after make-safe by electrician (Elec Notes 1, 2; ED113F/G Note 1)
15 | Remove existing fire alarm devices shown for demolition, 24 EA (FAD111F/G, FAD112F/G)
16 | Carry all debris down from Level 2 by stair (no elevator), haul out nightly; account for all tools and debris at end of each shift per Corrections requirements (RFI #40, #43; Spec 01 1100 1.9)
17 | Provide tacky mats, poly at openings and HEPA vacuums; leave work areas broom clean at the end of each shift (Spec 02 4113 1.4.G; Gen. Note W)
18 | Legally dispose of all demolition debris off-site; owner retains first right of refusal on salvage per joint damage survey (Gen. Notes D, L; Spec 02 4113 3.5)
ALTERNATES
1 | ALTERNATE #1: Remove 8" solid grouted CMU chase walls - Level 1 +/-166 LF (+/-1,770 SF) and Level 2 +/-62 LF (+/-560 SF); cut dowels flush where slab remains, following EOR field review (Struct Notes 1, 4; Plan Notes D01, D02)
2 | ALTERNATE #2: Sawcut and remove 4" slab-on-grade, thickened slab, footings and continuous bars, Unit F +/-555 SF / Unit G +/-569 SF (Struct Note 3; Plan Notes D11, D13; SD501 A4, A6)
3 | ALTERNATE #3: Wall / slab cuts for new plumbing 9 EA, partial wall demo for new door 1 EA, 12" openings in precast wall panels 4 EA, precast mezzanine slab openings 2 EA, roof panel / metal deck openings 3 EA, incl. GPR / X-ray scanning allowance (Plan Notes D03, D10; SD112F/G, SD121, SD501; RFI #32)
4 | ALTERNATE #4: Grind dowels / wall base down 1/2" minimum below top of slab where slab remains (Struct Note 4)
5 | ALTERNATE #5: Negative air machines and full-height poly dust containment, Units F & G
6 | ALTERNATE #6: Daytime work (Spec 01 2300 Alternate No. 1) - DDD price unchanged (flat labor rate)
EXCLUSIONS
- All patching, repair, slab repair per specs, roof patching, curbs and caps, fireproofing repair, and prep for new finishes (Spec 01 7329; Mech Note 2; RFI #21)
- Excavation, trenching and backfill below slab; disconnecting / capping / grout-abandoning underslab and below-grade piping (Plumbing Notes 2, 4, 5)
- Disconnect, cap and make-safe of all utilities - electrical, plumbing, chilled water, sprinkler drain-down and impairment, and fire alarm system programming / bypass by the respective trades
- Removal of conduit and wiring beyond the nearest junction box or back to the panel / source (Elec Gen. Note 4)
- Shoring: included is limited to non-load-bearing masonry; load-bearing wall shoring, shoring design, structural engineering, PE survey and stamped drawings excluded (RFI #46; Spec 02 4113 3.1.C; S001)
- Furnishing / installing lintels, bearing plates, jamb reinforcement, security bars at penetrations, and grouting (RFI #76)
- Plywood / steel security covers at openings left overnight, temporary partitions and guardrails by GC (01 1100 1.9)
- Hazardous materials (asbestos, lead, PCB ballasts) identification, abatement or disposal - no survey provided
- Crane or rooftop rigging for RTUs / fans; detention equipment and security systems (RFI #79, #82)
- Domestic Water Piping Replacement project (FDC_DW drawings) and ACT grid / tile removal and replacement
- Items to remain: existing fixtures to remain (Plumbing Note 6), existing lights in dayroom, equipment within NIC rooms, roof curbs and security bars
TERMS
- Bid based on plans and specifications only; quantities scaled and +/- (field verify).
- Zero retainage; net 30; price valid 90 days.
- Mobilization not included in unit pricing; each additional mobilization (e.g., Unit F and Unit G phased separately) $3,250.
- Night work Mon-Fri included at no premium; weekend work only with Corrections' written approval.
- Security time, escorts and FDLE background checks for DDD crew included as listed; delays from inmate movement, lockdowns or denied access are by change order.