## Summary & Scope
PALMS MEDICAL GROUP - LAKE SHORE REMODEL ¦ DEMOLITION + FLOORING
351 NE Franklin St, Lake City FL 32055 ¦ Owner: Lake Shore Hospital Authority ¦ 8,616 GSF outpatient clinic
PRICE SUMMARY
Demolition - Base bid (interior + site) - Disassemble Dynamics | 52140.8875
Demolition - Alt #1 exterior CMU walls | 8055.75
Demolition - Alt #2 sawcutting at site demo limits | 1525
Demolition - Alt #3 mastic removal / grinding | 9244.75
Flooring - Wayne's Carpet Plus | 57897.9375
Combined base (demo base + flooring) | 110038.825
SCOPE OF WORK
DEMOLITION SCOPE OF WORK (Disassemble Dynamics)
1. Complete interior demolition of all items in the building except roof drains above ceiling, main MDP and panels; remove interior partitions to deck, +/-850 LF (A1 Demo Note)
2. Remove drywall on exterior walls down to fur channel, +/-3,500 SF (A1 Demo Note)
3. Remove ceilings and grid throughout, incl. M100 data room ceiling only, +/-7,700 SF (A1, M100 Note)
4. Remove existing floor finishes throughout, +/-7,590 SF (A1 Demo Note)
5. Remove doors, frames and hardware, +/-40 EA; casework, countertops and reception desk, +/-100 LF (A1)
6. Remove plumbing fixtures, +/-30 EA, after capping by plumbing contractor (A1)
7. Remove light fixtures, devices, conduit and wire back to the nearest junction box; HVAC ductwork, diffusers, grilles and hangers (A1 Demo Note)
8. Remove existing storefront and glazing at new entrance and center section for new exterior door, +/-60 LF (A1, A1.1)
9. Remove existing curb and gutter 274 LF, asphalt pavement 1,574 SF, concrete 489 SF (Site Demo Notes 1, 2, 3)
10. Remove existing trees incl. stump grinding, 8 EA (Site Demo Note 4)
11. Protect X-Ray 120, MDP/panels and roof drains in place; legally dispose of all debris; leave broom clean
ALTERNATES
Alt #1: Remove exterior CMU walls at angled entries, +/-67 LF x +/-12' (A1 'Demo exterior CMU wall')
Alt #2: Sawcut asphalt / concrete / curb at site removal limits
Alt #3: Grind / remove mastic after flooring removal
DEMOLITION EXCLUSIONS
- X-Ray 120 (no demo this room); MDP, panels and roof drains to remain
- All patching, repair, floor leveling and prep for new finishes; utility disconnects/caps by trades
- Removal of conduit/wire beyond the nearest junction box or back to panel
- Shoring limited to non-load-bearing masonry; load-bearing shoring, design and engineering excluded; lintels/jamb reinforcement excluded
- Hazardous materials survey/abatement; erosion control, grading, utilities and new site work
- Terms: plans only, zero retainage, net 30, price valid 90 days; additional mobilization $3,250
FLOORING SCOPE (Wayne's Carpet Plus)
1. Furnish & install Mohawk 559 Anodized Lapis carpet tile in rooms per Finish Schedule incl. corridors, +/-4,948 SF
2. Furnish & install Flexco Natural Elements American Cherry 610 LVT in rooms per Finish Schedule, +/-3,147 SF
3. Furnish & install 2x2 sheet ceramic shower floor tile in ADA Tlt 124, +/-13 SF (color with PMG)
4. Floor prep - patch/skim allowance; transition strips between dissimilar floors (max 1/8")
FLOORING EXCLUSIONS
- Wood base WM618 / WM725, quarter round, chair rail and crown (trim carpentry); moisture mitigation beyond allowance; furniture moving

## Inputs
Palms Medical Group / Lake Shore Hospital Authority - 351 NE Franklin St, Lake City FL ¦ Estimate Inputs
Blue = editable input. Yellow = assumption to confirm. All costs flow to the estimate tabs.
Input | Value | Note
DEMOLITION (Disassemble Dynamics)
Labor rate ($/MH, flat) | 25 | Standing input
Crew size (men) | 6 | Local - Lake City, daytime
Shift length (hrs) | 8
Profit ($ per crew-day) | 1000 | Standing input
Contingency (% of direct) | 5% | Standing input
C&D dumpster 30 yd ($/pull) | 450 | Lake City rate not on file - confirm with hauler
Concrete/asphalt dumpster 20 yd ($/pull) | 450 | Lake City rate not on file - confirm
FLOORING (Wayne's Carpet Plus)
CT - Mohawk 559 Anodized Lapis material ($/SF) | 3.25 | Assumed carpet tile - get distributor quote
CT adhesive / release ($/SF) | 0.2
CT install labor ($/SF) | 0.85
CT waste factor | 7%
LVT - Flexco Natural Elements American Cherry 610 material ($/SF) | 3.5 | Get Flexco distributor quote
LVT adhesive ($/SF) | 0.25 | Per Flexco recommended adhesive
LVT install labor ($/SF) | 1.4
LVT waste factor | 8%
Shower floor tile 2x2 sheet ceramic - material incl. setting & grout ($/SF) | 14 | Color w/ PMG
Shower floor tile install ($/SF) | 18 | Small area - see minimum
Shower tile minimum charge ($) | 650
Floor prep / patch & skim allowance ($/SF of floor) | 0.45 | Existing slab condition unknown until demo
Transition strips ($/EA installed) | 65 | Gen. Note 2 & 3
Freight / delivery ($) | 450
Overhead & profit markup (Wayne's) | 25% | Set Wayne's margin

## Demo Bid - DDD
DISASSEMBLE DYNAMICS, INC. - DEMOLITION BID BREAKOUT
Remodel & Alterations - Lake Shore Hospital Authority / Palms Medical Group, 351 NE Franklin St, Lake City FL (TCCS plans 08/10/2026; site plan 02/02/2026)
Quantities scaled from A1 / A1.1 / A5 and taken from civil Demolition Notes & Estimated Quantities - verify in field. | [11 empty] | DEMOLITION MARKUPS - A1 DEMO PLAN, A1.1 STOREFRONT, SITE DEMO, FLOOR REMOVAL, CEILING REMOVAL
# | Description | Ref | Qty | Unit | MH / Unit | MH | Labor $ | Equip / Rental $ | Disposal $ | Other $ | Direct $
BASE BID - INTERIOR SELECTIVE DEMOLITION (COMPLETE GUT)
D1 | Remove interior partitions (stud & drywall) to deck, incl. framing | A1 complete demo note | 850 | LF | 0.25 | 212.5 | 5312.5 | 0 | 0 | 0 | 5312.5
D2 | Remove drywall on exterior walls down to fur channel | A1 complete demo note | 3500 | SF | 0.012 | 42 | 1050 | 0 | 0 | 0 | 1050
D3 | Remove ceilings & grid throughout (incl. M100 data room ceiling only) | A1; M100 note; Ceiling Removal markup | 7700 | SF | 0.012 | 92.4 | 2310 | 0 | 0 | 0 | 2310
D4 | Remove existing floor finishes (DDD-owned scraper) | A1; Floor Removal markup | 7590 | SF | 0.012 | 91.08 | 2277 | 0 | 0 | 0 | 2277
D5 | Remove doors, frames & hardware | A1 | 40 | EA | 1 | 40 | 1000 | 0 | 0 | 0 | 1000
D6 | Remove casework, countertops & reception desk | A1 | 100 | LF | 0.3 | 30 | 750 | 0 | 0 | 0 | 750
D7 | Remove plumbing fixtures (WC, lav/exam sinks, shower, mop sink) - after cap by plumber | A1 | 30 | EA | 1.5 | 45 | 1125 | 0 | 0 | 0 | 1125
D8 | Remove light fixtures, devices, conduit & wire back to nearest J-box (MDP & panels remain) | A1 complete demo note | 7700 | SF | 0.008 | 61.6 | 1540 | 0 | 0 | 0 | 1540
D9 | Remove HVAC ductwork, diffusers, grilles & hangers (roof drains remain) | A1 complete demo note | 7700 | SF | 0.008 | 61.6 | 1540 | 0 | 0 | 0 | 1540
D10 | Remove existing storefront & glazing (new entrance + center section) | A1, A1.1 | 60 | LF | 0.5 | 30 | 750 | 0 | 0 | 0 | 750
D11 | Load-out, protection of X-ray 120 & MDP, broom clean | A1 | 1 | LS | 40 | 40 | 1000 | 0 | 0 | 0 | 1000
D12 | Small equipment rental - debris carts & rolling scaffolds (2) for ceiling / high work | - | 16 | DAY | 0 | 0 | 0 | 800 | 0 | 0 | 800
D13 | Consumables - saw blades, debris bags, poly, floor protection, PPE | - | 1 | LS | 0 | 0 | 0 | 0 | 0 | 900 | 900
D14 | C&D disposal - 30 yd dumpsters | - | 8 | PULL | 0 | 0 | 0 | 0 | 3600 | 0 | 3600
| INTERIOR BASE BID - man-hours / crew-days |  |  |  |  | 746.18 | 16
| Direct cost | [9 empty] | 23954.5
| Contingency | [9 empty] | 1197.725
| Profit ($/crew-day x crew-days) | [9 empty] | 16000
| INTERIOR BASE BID TOTAL | [9 empty] | 41152.225
BASE BID - SITE DEMOLITION
S1 | Remove existing asphalt pavement | Site Demo Note 2 | 1574 | SF | 0.01 | 15.74 | 393.5 | 0 | 0 | 0 | 393.5
S2 | Remove existing concrete | Site Demo Note 3 | 489 | SF | 0.03 | 14.67 | 366.75 | 0 | 0 | 0 | 366.75
S3 | Remove existing curb & gutter | Site Demo Note 1 | 274 | LF | 0.08 | 21.92 | 548 | 0 | 0 | 0 | 548
S4 | Remove existing trees incl. stump grinding & haul-off | Site Demo Note 4 | 8 | EA | 6 | 48 | 1200 | 0 | 0 | 0 | 1200
S5 | Skid steer w/ breaker (3 days) + mini-ex (2 days) + stump grinder (2 days) | - | 1 | LS | 0 | 0 | 0 | 2850 | 0 | 0 | 2850
S6 | Concrete / asphalt disposal - 20 yd dumpsters (+/-72 tons) | - | 3 | PULL | 0 | 0 | 0 | 0 | 1350 | 0 | 1350
S7 | Tree / vegetative debris haul-off | - | 2 | LOAD | 0 | 0 | 0 | 0 | 900 | 0 | 900
| SITE BASE BID - man-hours / crew-days |  |  |  |  | 100.33 | 3
| Direct cost | [9 empty] | 7608.25
| Contingency | [9 empty] | 380.4125
| Profit ($/crew-day x crew-days) | [9 empty] | 3000
| SITE BASE BID TOTAL | [9 empty] | 10988.6625
ALTERNATE #1 - EXTERIOR CMU WALL REMOVAL (ANGLED ENTRIES)
A1.1 | Remove exterior CMU walls at angled entries (+/-67 LF x +/-12') | A1 'Demo exterior CMU wall' | 804 | SF | 0.15 | 120.6 | 3015 | 0 | 0 | 0 | 3015
A1.2 | Wall saw / chainsaw rental & blades | - | 2 | DAY | 0 | 0 | 0 | 900 | 0 | 0 | 900
A1.3 | CMU disposal - 20 yd dumpsters | - | 2 | PULL | 0 | 0 | 0 | 0 | 900 | 0 | 900
| ALT #1 - man-hours / crew-days |  |  |  |  | 120.6 | 3
| Direct cost | [9 empty] | 4815
| Contingency | [9 empty] | 240.75
| Profit ($/crew-day x crew-days) | [9 empty] | 3000
| ALT #1 TOTAL | [9 empty] | 8055.75
ALTERNATE #2 - SAWCUTTING AT SITE DEMO LIMITS
A2.1 | Sawcut asphalt / concrete / curb at removal limits | Site Demo | 200 | LF | 0.05 | 10 | 250 | 250 | 0 | 0 | 500
| ALT #2 - man-hours / crew-days |  |  |  |  | 10 | 1
| Direct cost | [9 empty] | 500
| Contingency | [9 empty] | 25
| Profit ($/crew-day x crew-days) | [9 empty] | 1000
| ALT #2 TOTAL | [9 empty] | 1525
ALTERNATE #3 - MASTIC REMOVAL / GRINDING OF EXISTING FLOOR
A3.1 | Grind / remove mastic after flooring removal | A1 | 7590 | SF | 0.02 | 151.8 | 3795 | 1200 | 0 | 0 | 4995
| ALT #3 - man-hours / crew-days |  |  |  |  | 151.8 | 4
| Direct cost | [9 empty] | 4995
| Contingency | [9 empty] | 249.75
| Profit ($/crew-day x crew-days) | [9 empty] | 4000
| ALT #3 TOTAL | [9 empty] | 9244.75
DEMOLITION BID SUMMARY
| INTERIOR BASE BID | [5 empty] | 16 |  |  |  | 41152.225
| SITE BASE BID | [5 empty] | 3 |  |  |  | 10988.6625
| ALT #1 | [5 empty] | 3 |  |  |  | 8055.75
| ALT #2 | [5 empty] | 1 |  |  |  | 1525
| ALT #3 | [5 empty] | 4 |  |  |  | 9244.75
| Base bid (interior + site) | [9 empty] | 52140.8875
| Base bid + all alternates | [9 empty] | 70966.3875
EXPENSE BREAKDOWN BY COST TYPE
| Section | Labor MH | Labor $ | Equipment $ | Disposal $ | Other / Consumables $ | Contingency $ | Profit $ | Total $
| INTERIOR BASE BID | 746.18 | 18654.5 | 800 | 3600 | 900 | 1197.725 | 16000 | 41152.225
| SITE BASE BID | 100.33 | 2508.25 | 2850 | 2250 | 0 | 380.4125 | 3000 | 10988.6625
| ALT #1 | 120.6 | 3015 | 900 | 900 | 0 | 240.75 | 3000 | 8055.75
| ALT #2 | 10 | 250 | 250 | 0 | 0 | 25 | 1000 | 1525
| ALT #3 | 151.8 | 3795 | 1200 | 0 | 0 | 249.75 | 4000 | 9244.75
| Base bid (interior + site) | 846.51 | 21162.75 | 3650 | 5850 | 900 | 1578.1375 | 19000 | 52140.8875
| Base bid + all alternates | 1128.91 | 28222.75 | 6000 | 6750 | 900 | 2093.6375 | 27000 | 70966.3875
| % of base bid |  | 40.59% | 7% | 11.22% | 1.726% | 3.027% | 36.44% | 100%
| Unit check - interior base bid $ per building SF (8,616 GSF) | [9 empty] | 4.7763
Note on B9: Assumed ACT grid ceilings - verify; drywall ceilings add labor
Note on B10: Existing floor type unknown; mastic grinding = Alt #3
Note on B31: Incl. 20" magnolia and 30"+ hardwoods
Note on B42: Verify load-bearing condition with EOR; shoring of load-bearing walls excluded

## Flooring - Wayne's
WAYNE'S CARPET PLUS - FLOORING ESTIMATE
Palms Medical Group / Lake Shore Hospital Authority - 351 NE Franklin St, Lake City FL ¦ A5 Finish Plan & Finish Schedule
FLOORING MARKUP - A5 FINISH PLAN (CT / LVT / shower tile by room)
Item | Description | Net Qty | Unit | Waste | Order Qty | Material $/U | Labor $/U | Material $ | Labor $ | Total $
F1 | Carpet tile - Mohawk 559 Anodized Lapis (CT rooms + corridors) | 4948 | SF | 7% | 5295 | 3.45 | 0.85 | 18267.75 | 4205.8 | 22473.55
F2 | LVT - Flexco Natural Elements American Cherry 610 (glue-down) | 3147 | SF | 8% | 3399 | 3.75 | 1.4 | 12746.25 | 4405.8 | 17152.05
F3 | 2x2 sheet ceramic shower floor tile - ADA Tlt 124 | 13 | SF |  | 13 | 14 | 18 | 182 | 234 | 650
F4 | Floor prep - patch / skim after demo (allowance) | 8095 | SF |  | 8095 |  | 0.45 | 0 | 3642.75 | 3642.75
F5 | Transition strips between dissimilar floors (max 1/8") | 30 | EA |  | 30 |  | 65 | 0 | 1950 | 1950
F6 | Freight / delivery | 1 | LS |  | 1 | 450 |  | 450 | 0 | 450
| Subtotal (material + labor) | [8 empty] | 46318.35
| Overhead & profit | [8 empty] | 11579.5875
| FLOORING TOTAL - WAYNE'S CARPET PLUS | [8 empty] | 57897.9375
| Price per SF of flooring | [8 empty] | 7.1523
Room takeoff (from A5 markup)
| Room / area | SF | Finish
| 122 Break/Conf | 633 | CT
| 123 ADA Tlt | 62 | LVT
| 124 ADA Tlt | 90 | LVT
| 125 Provider | 102 | CT
| 126 Sto | 24 | LVT
| 128/130/132 Exam | 308 | LVT
| 127 Provider | 103 | CT
| 129/131/133 Exam | 325 | LVT
| Corridor C01 | 564 | CT
| Corridor N entry | 56 | CT
| Corridor link | 47 | CT
| Corridor C02 | 776 | CT
| Corridor C03 | 120 | CT
| Corridor C04 | 111 | CT
| 121/121A Office/Sto | 188 | CT
| 120 X-Ray | 148 | LVT
| Alcove @ C02 | 77 | CT
| 118 Nurse Pod | 172 | CT
| 119 Office | 174 | CT
| 112-117 Offices | 520 | CT
| 111 Steril / 109 ADA | 124 | LVT
| 110 Nurse Sta | 146 | LVT
| 148 Jan | 36 | LVT
| 108 Lab | 181 | LVT
| 105/106 Triage | 122 | LVT
| 107 Mech | 112 | LVT
| 103 Vestibule | 65 | LVT
| 104 ADA Tlt | 58 | LVT
| 100 Waiting / 101 Recep | 870 | CT
| 102 Pharmacy | 348 | LVT
| 134-144 Exam (6) | 636 | LVT
| 145 Provider | 103 | CT
| 146 Sto | 27 | LVT
| 135/137/139 Office/Prov | 333 | CT
| 141/143/147 Exam | 335 | LVT
Note on B7: Small-area minimum applied

## Markup - Flooring A5
MARKUP: Flooring A5 (full-size PDF: PMG_Lake_Shore_Markups.pdf)

## Markup - Demo A1
MARKUP: Demo A1 (full-size PDF: PMG_Lake_Shore_Markups.pdf)

## Markup - Demo A1.1
MARKUP: Demo A1.1 (full-size PDF: PMG_Lake_Shore_Markups.pdf)

## Markup - Site Demo
MARKUP: Site Demo (full-size PDF: PMG_Lake_Shore_Markups.pdf)

## Markup - Floor Removal
MARKUP: Floor Removal (full-size PDF: PMG_Lake_Shore_Markups.pdf)

## Markup - Ceiling Removal
MARKUP: Ceiling Removal (full-size PDF: PMG_Lake_Shore_Markups.pdf)